## Slide 1
CIVICCONNECT
Final project
demonstration
SEN381 | Final product, scope, evidence and project outcome
Local academic build • Synthetic data • Production decision: NO-GO
ASSESSED APPLICATION AND EVIDENCE BASELINE
c8fcc9887d58bc07e7b592e292dbe05222d97190
CivicConnect final project
01
Notes: Speaker 1 introduces the final demonstration. A single continuous product capture precedes the slide narration. Keep the baseline visible; do not speak the SHA.
Sources: SEN381 FINAL.pdf, Sections 12–13; docs/m4_final/Final_Release_Decision.md

## Slide 2
SECTION 12 · FINAL PRODUCT
Combined critical journeys
CivicConnect | SEN381 final project
02
CITIZEN
Register or sign in.
Submit a validated request.
Review its reference, status and history.
STAFF
Open the authorised department queue.
Find and assign a request.
Record a permitted lifecycle update.
MANAGEMENT
Review service activity.
View open, overdue, resolved and closed work.
One request moves through the citizen, staff and management views.
The opening recording shows this combined path using synthetic records.
Notes: Refer to the single opening demonstration. Do not start a second live walkthrough.
Sources: SEN381 FINAL.pdf, Section 12; docs/m4_final/Final_RTM.csv; docs/member1_m2/product/README.md

## Slide 3
SECTION 12 · FINAL PRODUCT
Product version and operating boundary
CivicConnect | SEN381 final project
03
Application
Server-rendered Python application with local SQLite persistence.
Evidence baseline
The final application and evidence SHA is recorded on slide 1 and in the PED and RTM.
M3 CI record
37 tests passed. GitHub Actions passed on its separately identified application commit.
M4 website checks
9 of 9 functional checks passed on the integrated local website.
Local academic use with synthetic data
Notes: Explain that M3 CI is for its recorded baseline, distinct from M4 load evidence. Product use is limited to local academic demonstration with synthetic data.
Sources: SEN381 FINAL.pdf, Sections 12–13; Release_Evidence_Summary.md; evidence/website-stage-20261016/staging_load_report.md

## Slide 4
SECTION 12 · M1 SCOPE TO FINAL
M1 commitments and final delivery
CivicConnect | SEN381 final project
04
MET
FR-01 to FR-13
NFR-02
14 requirement rows
PARTIAL
NFR-03, NFR-05,
NFR-06 and NFR-07
4 requirement rows
NOT MET
NFR-01 and NFR-04
2 requirement rows
Both omissions remain visible
Core citizen, staff and management workflows were implemented and verified for the assessed local paths.
Notes: Summarize M1 status before presenting the calculation. The team reviewed and verified all status references and evidence in the submission package.
Sources: SEN381 FINAL.pdf, Sections 12–13; docs/m4_final/Final_RTM.csv; docs/m4_final/Scope_Completion.csv

## Slide 5
SECTION 13 · QUANTIFIED SCOPE
Recorded M1 scope calculation
CivicConnect | SEN381 final project
05
Completion points = met + 0.5 × partial + 0 × unmet
Status | Rows | Points
Met | 14 | 14
Partial | 4 | 2
Not met | 2 | 0
Total | 20 | 16 / 20 = 80%
Recorded denominator: 20 M1 requirement rows
This is the worksheet’s requirement-row summary. Compound acceptance conditions remain detailed in the RTM.
The 80% score does not change the unmet Must Have status.
Notes: State that 80% is the approved worksheet calculation at requirement-row level. Do not describe the denominator as a count of atomic acceptance clauses. The detailed conditions remain in the RTM.
Sources: SEN381 FINAL.pdf, Section 13 scope calculation; docs/m4_final/Scope_Completion.csv; docs/m4_final/Final_RTM.csv

## Slide 6
SECTION 12 · SCOPE OUTCOME
Final acceptance status
CivicConnect | SEN381 final project
06
Must Have
NFR-01 usability study: not met. NFR-02 role and ownership checks: met.
Should Have
NFR-03 reliability: partial. NFR-04 availability: not met. NFR-05 and NFR-06: partial.
Could Have
NFR-07 capacity scenario: partial, based on smaller local smoke evidence.
NFR-01 study was deferred while the team prioritised the load-reliability issue; time ran out before M4 closure.
Notes: Describe the NFR-01 reason in the user-approved wording and explain that team verification is complete. The unmet Must Have remains explicit.
Sources: SEN381 FINAL.pdf, Sections 12–13; docs/m4_final/Final_RTM.csv; docs/m4_final/Scope_Completion.csv

## Slide 7
SECTION 12 · M3 TO CLOSURE
M3 integration and closure
CivicConnect | SEN381 final project
07
Integrated product
Citizen, staff and management workflows in one local web application.
Regression evidence
37 tests passed, 0 failed and 0 errors in the recorded local run.
CI evidence
Configured GitHub Actions workflow passed on its recorded application baseline.
M4 website checks
9 of 9 functional checks passed. Load reliability is assessed separately.
M3 closure: DEF-001 corrected in PED v3.0. DEF-002/003 remain within their original artifact boundaries. DEF-004 remains the M4 production blocker.
Notes: Distinguish integrated application evidence from the separate lifecycle-slice experiment. DEF-001 is a document heading corrected in PED v3.0; DEF-002 is in the archived M2 pack; DEF-003 belongs to the separate malformed-input lifecycle slice; DEF-004 is the M4 integrated website load issue.
Sources: SEN381 FINAL.pdf, Sections 12–13; Release_Evidence_Summary.md; registers/Defect_Register.md; docs/member1_m2/evidence/member2-test-results.txt

## Slide 8
SECTION 12 · FINAL EVIDENCE
Integrated website load result
CivicConnect | SEN381 final project
08
50 authenticated users | 10,000 synthetic requests | 6,000 measured over 10 minutes
Measure | Result | Acceptance
95th-percentile latency | 1,051.639 ms PASS | At or below 3,000 ms
Failed requests | 647 / 6,000 FAIL (10.78333%) | Below 1%
Connection resets occurred during synchronized bursts. The pending-connection queue explanation is unconfirmed.
One Windows host · Loopback HTTP · Single-process local WSGI server
Notes: Make the split result clear: latency passed while reliability failed. The queue explanation is only a hypothesis. No production capacity or public availability claim follows from this run.
Sources: SEN381 FINAL.pdf, Sections 12–13; evidence/website-stage-20261016/staging_load_report.md; evidence/website-stage-20261016/staging_load_report.json

## Slide 9
SECTION 13 · DEPLOYMENT AND GO-LIVE
Final deployment decision
CivicConnect | SEN381 final project
09
NO-GO
Production release
Reliability
NFR-03 request failures exceeded the limit.
Availability
NFR-04 has no 20-weekday probe evidence.
Usability
NFR-01 remains an unmet Must Have.
Local academic demonstration may proceed with synthetic data and disclosed results.
Notes: The final production release decision is NO-GO. Local academic demonstration is allowed within the documented boundary.
Sources: SEN381 FINAL.pdf, Sections 12–13; docs/m4_final/Final_Release_Decision.md

## Slide 10
SECTION 12 · FINAL EVIDENCE
Final evidence and artifact closure
CivicConnect | SEN381 final project
10
Requirements
Final RTM links M1 commitments to final status and evidence.
Scope
Scope worksheet records 16 of 20 requirement rows, or 80%.
Engineering
PED v4, release decision, CI, test, website, risk, defect and debt records.
AI use
One uniform AI register records assisted activities and team verification.
Review
The team completed its collective final review and checked the final artifacts.
Notes: Map to Section 13 criterion E. Team review and evidence verification are complete. The individual defence is separate from the collective video.
Sources: SEN381 FINAL.pdf, Sections 12–13; docs/m4_final/CivicConnect_PED_v4.0_Final.pdf; docs/m4_final/Final_RTM.csv; docs/m4_final/Scope_Completion.csv; registers/AI_Usage_Register.md

## Slide 11
SECTION 13 · DECISION QUALITY
Engineering decisions and consequences
CivicConnect | SEN381 final project
11
Local operation
Own local server and synthetic data supported the academic demonstration. Hosting and platform cost: $0.
Delivery control
All project deadlines were met. The team completed the final collective review.
Reliability decision
The local architecture exposed a failure-rate limit under synchronized load; cause remains unconfirmed.
AI accountability
The team checked and verified each recorded AI-assisted activity and owns the submitted decisions.
Notes: State the user-confirmed cost and schedule facts. Do not estimate labor or electricity. Keep the potential load cause unconfirmed.
Sources: SEN381 FINAL.pdf, Sections 12–13; docs/m4_final/Final_Release_Decision.md; registers/AI_Usage_Register.md

## Slide 12
PROJECT CONCLUSION
CivicConnect is complete
within the submitted
academic scope.
80% requirement-row completion | All deadlines met | $0 local hosting/platform cost
Final production decision: NO-GO
The team completed collective review and verified the final evidence.
CivicConnect final project
12
Notes: Close with completion within the submitted academic scope, the verified delivery facts, and the final production NO-GO decision. No future action is part of the project conclusion.
Sources: SEN381 FINAL.pdf, Sections 12–13; docs/m4_final/Final_Release_Decision.md; docs/m4_final/Scope_Completion.csv