# CivicConnect Project Engineering Document

Milestone 1 Engineering Foundation and Requirements Review Candidate v0.10

This PED defines stakeholder needs, committed capabilities, measurable acceptance targets, constraints, risks and controls for the four-person team. Version 0.10 corrects the M1 review findings and links repository evidence. Formal v1.0 baseline approval requires the human verification and sign-off records in Sections 18 and 24.

# 1. Problem / Business Need

CivicConnect is intended to improve communication between citizens and the organisations responsible for providing public services. At present, communication and service requests can be fragmented or inefficient, making it difficult for citizens to submit requests, receive feedback and keep track of their progress. This can also make it more difficult for organisations to manage requests consistently and ensure that the correct information reaches the appropriate staff.

CivicConnect aims to address this by providing a centralised digital platform where citizens can submit relevant requests or information, monitor their progress and receive feedback. From the organisation's perspective, the platform will provide a more organised way of receiving, reviewing and managing citizen interactions, while ensuring that authorised staff have access to the information they need.

The value of CivicConnect therefore goes beyond simply introducing a new software system. Its purpose is to create a more effective connection between citizens and service providers, with the aim of improving accessibility, efficiency, transparency and accountability in the delivery and management of public services.

# 2. Stakeholders Analysis

| # Stakeholder | # Primary Need / Expectation | # Influence | # Interest |
| --- | --- | --- | --- |
| # Citizens / End Users | # Simple and accessible way to interact with CivicConnect, submit information/requests and receive feedback | # Medium | # High |
| # Municipality / Organisation | # Reliable platform that supports communication and effective service management | # High | # High |
| # System Administrators | # Ability to manage users, permissions and administrative information | # High | # Medium |
| # Operational Staff | # Accurate and organised information that allows requests to be processed and updated efficiently | # Medium | # High |
| # Project Client / Representative | # System must satisfy the agreed business needs, scope, quality expectations and project constraints | # High | # High |
| Management / oversight | Identify outstanding and overdue work and accountable request owners | High | High |

# 3. Main Stakeholder Needs

| Stakeholder | Basic Need / Expectation |
| --- | --- |
| Citizens / end users | An easy-to-use way to interact with CivicConnect and receive feedback or updates. |
| Staff | Organised, accurate information that allows requests or issues to be managed efficiently. |
| System administrators | Control over users, system information and administrative functions. |
| Responsible organisation | A reliable system that can improve communication and service delivery. |
| Management / oversight | Useful service-activity information for accountability and performance analysis. |

# 4. Basic Scope

In Scope:

| In-Scope Capability | Reason |
| --- | --- |
| User access to CivicConnect | Enables identified users to interact with the system |
| Submission of relevant requests/information | Supports the primary interaction between citizens and the organisation |
| Viewing submission/request status | Provides users with feedback and improves transparency |
| Staff access to relevant submissions | Allows authorised personnel to process citizen interactions |
| Updating relevant request/status information | Allows submissions to progress through the required process |
| Basic user/role administration | Provides appropriate control over system access |
| Input validation | Supports information quality and reduces invalid submissions |
| Controlled categories | Consistent request classification |
| History and lifecycle feedback | Earlier requests and accepted/rejected/completed outcomes |
| Staff search, details and assignment | Find work and identify accountable ownership |
| Controlled transitions and closure | Valid updates and authorised completion |
| Basic oversight | Open, overdue, resolved and closed work by category/status |

Out of Scope:

| Out-of-Scope Item | Justification |
| --- | --- |
| Functionality unrelated to CivicConnect's defined business problem | Prevents unnecessary expansion of project scope |
| Replacement of unrelated external organisational systems | CivicConnect should address its defined problem rather than replace every existing system |
| Production deployment during M1 | M1 establishes the engineering foundation rather than production implementation |
| Final architecture and technology selection during M1 | These decisions require later evidence and analysis |
| Detailed database/API/UI implementation during M1 | These belong to later lifecycle activities |

- Deferred / Future Scope:

| Deferred Item | Reason for Deferral |
| --- | --- |
| Advanced reporting/analytics | Core operational requirements should be established first |
| Additional external-system integrations | Integration requirements and external dependencies require further evidence |
| Dedicated mobile application | Need, cost and technical implications should first be evaluated |
| Advanced automated notifications | Exact stakeholder and communication requirements must first be confirmed |
| Additional enhancement features | Should only enter scope after stakeholder value and project impact are analysed |

# 5. Possible Stakeholder Conflict

Citizens may want CivicConnect to be very simple and quick to use, while administrators and the responsible organisation may require additional information, validation and security. The project will therefore need to balance ease of use with sufficient control, security and data quality.

# 6. Functional Requirements (FRs)

The functional requirements below define the core capabilities CivicConnect must provide. Each requirement is uniquely identified, prioritised, linked to its originating stakeholder/source, and paired with measurable acceptance criteria so that it can be objectively verified later in the project lifecycle.

| ID | Functional Requirement | Priority | Source / Stakeholder | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| FR-01 | The system shall allow a citizen to register and log in with a unique account before submitting a request. | Must Have | Citizens / End Users | Valid unique registration creates one account and permits login. Duplicate identifiers are rejected. Invalid credentials create no authenticated session; valid credentials access the correct account. |
| FR-02 | The system shall allow a citizen to submit a service request or piece of information through a structured form. | Must Have | Citizens / End Users (Problem & Business Need) | A valid title, description, location and active category are saved with requester identity and submission time; a unique reference is displayed. Missing or invalid required values create no request. See Section 19. |
| FR-03 | The system shall allow a requester to view a history of all their submitted requests and each current status. | Must Have | Citizens / End Users | Given three own requests in different states, the requester can list and open all three with correct statuses. Another requester cannot access them through the UI or direct requests. |
| FR-04 | The system shall allow authorised operational staff to view submissions assigned to them or their department. | Must Have | Operational Staff | A staff member logged in with the Staff role sees only submissions relevant to their department; unauthorised submissions are not visible or accessible. |
| FR-05 | The system shall allow authorised staff to update the status and add remarks to a citizen's request. | Must Have | Operational Staff | A permitted update saves status, remark, actor and timestamp. Refreshing within 5 seconds shows the saved state to the requester. Invalid transitions do not alter the record; see FR-13. |
| FR-06 | The system shall allow administrators to create, edit and deactivate accounts and assign roles, with updated access enforced on subsequent authenticated requests. | Must Have | System Administrators | An administrator can create an account, edit permitted details, deactivate it and assign/change roles. Deactivation and role changes take effect by the next authenticated request. Non-administrators cannot invoke these operations. |
| FR-07 | The system shall validate mandatory fields and reject a request submission if required information is missing or malformed. | Must Have | Citizens / End Users; Municipality / Organisation | Missing or invalid title, description, location or category values are rejected with field-level errors. The same rules apply to direct submissions. No invalid record is saved; limits are defined in Section 19. |
| FR-08 | The system shall give requesters meaningful feedback when a request is accepted, rejected, updated or completed. | Must Have | Master brief Section 3 requester capabilities | Within 60 seconds of a saved lifecycle event, authenticated request history/details show status, event time and a requester-visible explanation. Rejection and resolution require explanations. Email/push transport remains optional. |
| FR-09 | The system shall provide authorised management users with basic service activity and accountability information. | Must Have | Master brief Section 3 management capabilities | For a known dataset and selected submission-date range, counts and lists correctly identify open, overdue, resolved and closed requests by category/status, with assignee and age visible. Unauthorised access is denied. See Section 19 definitions. |
| FR-10 | The system shall categorise requests using an active controlled category. | Must Have | Master brief Section 3 requester capabilities | Unknown/inactive categories are rejected. Administrators maintain the list; retirement preserves historical request category labels. |
| FR-11 | The system shall let authorised staff search, filter and sort relevant requests and view full details. | Must Have | Master brief Section 3 staff capabilities | Reference/title search and category/status/assignee filters return matching authorised records. Submitted-date/due-date sorting is correct. Details show description, location, owner, times and lifecycle actions; inaccessible records remain hidden. |
| FR-12 | The system shall let authorised staff assign or accept responsibility for a request. | Must Have | Master brief Section 3 staff capabilities | Staff can accept unassigned work or assign an eligible staff member. Assignee, actor and time are recorded. Ineligible/unauthorised assignments are rejected without changing ownership. |
| FR-13 | The system shall enforce controlled status transitions and record actions and resolution information. | Must Have | Master brief Section 3 staff capabilities | Permit Submitted to Accepted or Rejected; Accepted to In Progress; In Progress to Resolved; Resolved to Closed. Only authorised staff transition records. Acceptance requires an assignee and due time; rejection requires a reason and resolution requires a summary. Record actor/time/explanation. Reject all other transitions. |

# 7. Non-Functional Requirements (NFRs)

Non-functional requirements describe the quality attributes CivicConnect must meet. They are measurable rather than descriptive, and directly inform later architecture and technology decisions without pre-empting them at this stage.

| ID | Non-Functional Requirement | Priority | Source / Stakeholder | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| NFR-01 | Usability: The citizen-facing submission process shall be simple enough for a first-time user to complete without assistance. | Must Have | Citizens / End Users (Possible Stakeholder Conflict) | With five first-time representative users and the same valid scenario, at least four submit successfully within 5 minutes without assistance. Record individual times, errors and feedback. |
| NFR-02 | Security: Access to citizen personal information and request data shall be restricted according to the authenticated user's role. | Must Have | System Administrators; Municipality / Organisation | A user with the Citizen role cannot view, via the UI or a direct request, another citizen's submissions or personal data; role-based access is enforced on every relevant request. |
| NFR-03 | Performance: Status lookup shall meet the defined response-time target under the specified test load. | Should Have | Citizens / End Users; Operational Staff | With 50 concurrent authenticated users and 10,000 requests, each user performs one lookup every 5 seconds for 10 minutes after warm-up. At least 95% complete within 3 seconds; fewer than 1% fail. Record hardware/network conditions. |
| NFR-04 | Availability: The platform shall be available for citizen use during standard business hours with minimal unplanned downtime. | Should Have | Municipality / Organisation; Project Client / Representative | Over 20 weekdays, achieve at least 99% availability during 08:00–17:00 Africa/Johannesburg, measured by one-minute probes. Exclude only maintenance announced 24 hours ahead and report excluded minutes separately. |
| NFR-05 | Data Quality: The system shall enforce validation rules on all citizen-submitted data to reduce incomplete or malformed records. | Should Have | Operational Staff; Municipality / Organisation | All valid/invalid boundary cases for submission fields pass validation tests. An audit of 100 saved requests (or all if fewer) finds no missing mandatory or invalid-category values. |
| NFR-06 | Maintainability: The system's requirements, decisions and changes shall be traceable to support controlled maintenance after M1. | Should Have | Project Client / Representative (SEN381 Master Project Brief) | Each baselined requirement can be traced, via the RTM, to its source, its acceptance criteria and any linked design or test evidence added in later milestones. |
| NFR-07 | Scalability: The design shall support defined growth in users and requests while preserving lookup behaviour. | Could Have | Municipality / Organisation | At M2 assess 50,000 stored requests and 100 concurrent users against the same lookup pattern and 3-second 95th-percentile target. Record capacity assumptions and bottlenecks; load-test at M3. Resource/configuration increases are permitted with cost recorded. |

Prioritisation note: Requirements are prioritised using MoSCoW (Must Have / Should Have / Could Have). "Must Have" requirements are essential to the core problem defined in Section 1 and the in-scope capabilities defined in Section 4; "Should Have" requirements materially improve quality or usability but would not block a minimal working baseline; "Could Have" requirements add value but are the first candidates for deferral if constraints (schedule, resources) require trade-offs.

# 8. Initial Requirements Traceability Matrix (RTM)

The RTM below establishes live traceability from stakeholder/source through to each requirement and its acceptance criteria, and provides the structure to which later design, change and test evidence will be linked. It will be maintained and extended as a controlled artefact throughout the project.

| Req ID | Source / Stakeholder | Requirement Summary | Acceptance Criteria Ref. | Design Evidence | Test Evidence | Status |
| --- | --- | --- | --- | --- | --- | --- |
| FR-01 | Citizens / End Users | Account registration and login | FR-01 AC | Pending (M2) | Pending (M2) | Proposed for review |
| FR-02 | Citizens / End Users | Submit a service request | FR-02 AC | Pending (M2) | Pending (M2) | Proposed for review |
| FR-03 | Citizens / End Users | Own request history and status | FR-03 AC | Pending (M2) | Pending (M2) | Proposed for review |
| FR-04 | Operational Staff | View assigned submissions | FR-04 AC | Pending (M2) | Pending (M2) | Proposed for review |
| FR-05 | Operational Staff | Update request status/remarks | FR-05 AC | Pending (M2) | Pending (M2) | Proposed for review |
| FR-06 | System Administrators | Manage user accounts and roles | FR-06 AC | Pending (M2) | Pending (M2) | Proposed for review |
| FR-07 | Citizens / Organisation | Validate mandatory submission fields | FR-07 AC | Pending (M2) | Pending (M2) | Proposed for review |
| FR-08 | Citizens / End Users | Notify citizen of status change | FR-08 AC | Pending (M2) | Pending (M2) | Proposed for review |
| FR-09 | Organisation / Client | Basic request summary view | FR-09 AC | Pending M2 | Pending M3 | Proposed for review |
| NFR-01 | Citizens / End Users | Usable submission process | NFR-01 AC | Pending (M2) | Pending (M2) | Proposed for review |
| NFR-02 | Administrators / Organisation | Role-based access to data | NFR-02 AC | Pending (M2) | Pending (M2) | Proposed for review |
| NFR-03 | Citizens / Staff | Response time under normal load | NFR-03 AC | Pending (M2) | Pending (M2) | Proposed for review |
| NFR-04 | Organisation / Client | Platform availability | NFR-04 AC | Pending (M2) | Pending (M2) | Proposed for review |
| NFR-05 | Staff / Organisation | Data validation quality | NFR-05 AC | Pending (M2) | Pending (M2) | Proposed for review |
| NFR-06 | Project Client / Master Brief | Traceable, maintainable baseline | NFR-06 AC | This RTM | N/A at M1 | Proposed for review |
| NFR-07 | Organisation | Scalable data/access approach | NFR-07 AC | Pending M2 | Pending M3 | Proposed for review |
| FR-10 | Master brief Section 3 requester capabilities | The system shall categorise requests using an active controlled category. | FR-10 AC | Pending M2 | Pending M3 | Proposed for review |
| FR-11 | Master brief Section 3 staff capabilities | The system shall let authorised staff search, filter and sort relevant requests and view full details. | FR-11 AC | Pending M2 | Pending M3 | Proposed for review |
| FR-12 | Master brief Section 3 staff capabilities | The system shall let authorised staff assign or accept responsibility for a request. | FR-12 AC | Pending M2 | Pending M3 | Proposed for review |
| FR-13 | Master brief Section 3 staff capabilities | The system shall enforce controlled status transitions and record actions and resolution information. | FR-13 AC | Pending M2 | Pending M3 | Proposed for review |

"Design Evidence" and "Test Evidence" are intentionally recorded as Pending or Deferred candidate at M1, since detailed design and test execution fall outside the M1 boundary (Section 5 of the Milestone brief). Recording the structure now  rather than leaving it absent  is what allows later architecture, construction and verification evidence to be linked back to a specific requirement without re-engineering traceability retroactively.

# 9. Traced Requirement Example: Stakeholder → Requirement → Acceptance Criteria

To demonstrate that the RTM is genuinely usable and not only a table of identifiers, one requirement is traced end-to-end below, from its stakeholder source through to its measurable acceptance criteria.

| Traceability Step | Detail |
| --- | --- |
| Source / Stakeholder | Citizens / End Users — identified in the Stakeholder Analysis (Section 2) as needing "a simple and accessible way to interact with CivicConnect, submit information/requests and receive feedback". |
| Business Need Link | Directly supports the Problem/Business Need (Section 1): citizens currently struggle to submit requests and track their progress; CivicConnect must let them do both centrally. |
| Scope Link | Corresponds to the in-scope capability "Submission of relevant requests/information" and "Viewing submission/request status" in the Basic Scope (Section 4). |
| Requirement | FR-02 — The system shall allow a citizen to submit a service request or piece of information through a structured form. |
| Acceptance Criteria | A citizen can complete and submit a request containing all mandatory fields; on submission the system displays a confirmation reference number. |
| Related Requirements | Linked to FR-01 (a citizen must be registered/logged in to submit), FR-03 (the citizen must then be able to view the status of what was submitted) and FR-07 (mandatory fields must be validated before the submission is accepted). |
| Evidence Still to be Added | Design evidence (submission form design/data model) and test evidence (functional test confirming the confirmation reference is generated and stored) will be linked to FR-02 in the RTM from M2 onward, once architecture and construction begin. |

This trace shows the full chain currently available at M1: a named stakeholder need feeds a scoped capability, which is expressed as a uniquely identified, prioritised requirement with testable acceptance criteria, and is positioned in the RTM ready to receive design and test evidence in later milestones.

# 10. Project Constraints

This section records the formal constraints within which CivicConnect must be engineered and identifies their engineering implications. Constraints are not merely administrative boundaries; they directly influence requirements prioritization, scope decisions, and later architectural choices.

## 10.1 Scope Constraints

The scope baseline defined in Section 4 of this PED represents the formal constraint on what will be delivered. The explicit out-of-scope and deferred items are controlled constraints designed to prevent scope creep and preserve the project's focus on its core business need.

Engineering Implication: The team must prioritize features aligned with the "Must Have" and "Should Have" requirements identified in Section 6. Any request for work falling outside the formal scope baseline requires a formal change process through the Engineering Decision Log and reassessment of all other constraints. This directly supports the risk mitigation strategy for R-01 (Scope Creep).

## 10.2 Schedule Constraints

The project follows the SEN381 semester schedule, with Milestone 1 establishing the engineering baseline by the due date. The overall project lifecycle is bounded by the academic calendar, meaning time to complete M1 (Engineering Foundation), M2 (Architecture), and M3 (Construction and Verification), and M4 (Final Product and Engineering Defence) is fixed.

Engineering Implication: This schedule constraint forces the team to make deliberate scope decisions and to avoid premature implementation. The phased milestone approach is the primary control mechanism to ensure completion within the fixed period. This constraint supports deferring advanced analytics and implementation choices, while preserving all mandatory business capabilities including basic reporting.

Interaction with Other Constraints: The fixed schedule interacts with the cost/resource constraint. With four team members and a fixed deadline, the team cannot afford to over-engineer features or pursue overly ambitious technical solutions. This reinforces the need for the MoSCoW prioritization applied in the requirements section.

## 10.3 Cost and Resource Constraints

The project is delivered by a team of four students, with no external budget for third-party services, infrastructure, or tools beyond free-tier or university-provided resources. Team members effort is bounded by other academic commitments.

Engineering Implication: At M2 the team will compare viable technology options against cost, licensing, capability and environment constraints; no final stack is selected in M1. Team communication and task allocation must be managed efficiently via GitHub issues and the Team Working Agreement to maximize the limited human resource. The small team size also means that responsibilities must be clearly defined and that all members must be capable of understanding and defending all artefacts, as per the individual assessment requirements.

## 10.4 Quality Constraints

CivicConnect must be accepted by the assessor, who will evaluate the project against the criteria in the M1 brief and the SEN381 CivicConnect Master Project Brief. Quality is measured not only by functionality but by the presence of a controlled, traceable, and defensible engineering baseline.

Engineering Implication: The project must produce high-quality controlled artefacts (PED, RTM, Risk Register, Decision Log, AI Usage Register). The team cannot rely on "just getting it to work"; the engineering process and evidence are as important as the final code. This constraint is why NFR-06 (Maintainability) requires traceability and why the RTM has been established as a live artefact.

## 1.5 Security Constraints

CivicConnect manages potentially sensitive citizen information and requests. The system must therefore enforce role-based access control, ensure data confidentiality, and protect against common vulnerabilities from the outset.

Engineering Implication: Security cannot be an afterthought. The system design (in M2) must explicitly incorporate authentication, authorization, and data validation to satisfy NFR-02 (Access Control). The security constraints directly influence why FR-06 (User Management) is prioritized as a "Must Have" requirement—without it, role-based access control cannot be enforced. This constraint also influences the Forward Engineering Consideration of User Data Privacy (Section 12.6).

Interaction with Scope Constraints: The security constraint forces the system to have robust user and role management. This means that what might seem like an optional administrative feature is actually essential for compliance with NFR-02. The scope must therefore include adequate user management functionality.

## 10.6 Constraint Trade-offs and Interactions

A key engineering responsibility is to recognize that constraints do not exist in isolation. They interact and managing them often involves trade-offs.

| Constraint Pair | Nature of Interaction | Engineering Decision |
| --- | --- | --- |
| Quality vs. Schedule & Resources | The project has a strict schedule and a small team. Achieving the highest possible quality on all requirements is not feasible. | Preserve mandatory capabilities and quality targets; defer advanced enhancements when capacity is constrained. |
| Security vs. Usability | Citizens want a simple, quick process, but administrators require sufficient information, validation, and security. | The team has balanced this by ensuring mandatory fields are minimal yet sufficient and that security controls are enforced transparently in the background. |
| Scope vs. Resources | The team is small and cannot deliver every feature. | Scope Baseline explicitly excludes functionality unrelated to the core business problem and defers advanced features for future consideration. |
| Security vs. Schedule | Implementing robust security controls takes time and careful design. | Security requirements are designated "Must Have" to ensure they are addressed early, preventing costly rework later. This aligns with the Forward Engineering Consideration on User Data Privacy. |

The principal trade-off preserves minimum business capabilities and their acceptance criteria while deferring advanced analytics, additional integrations and a dedicated mobile application. Priority affects delivery order, not the quality required of delivered functionality. Basic reporting, validation and lifecycle feedback remain mandatory.

# 11. Initial Risk Register

The Risk Register below identifies project-specific risks that could threaten the successful completion of CivicConnect. Each risk is tested for probability and impact, assigned a priority, and provided with mitigation and contingency plans. The register is a live artefact that will be updated as the project progresses.

| ID | Risk Description | Probability | Impact | Priority | Mitigation | Contingency | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R-01 | Scope Creep: Uncontrolled addition of features or requirements beyond the baseline due to team members adding "nice-to-haves" or misinterpretation of stakeholder needs. | Medium | High | High | Strict adherence to the Scope Baseline; formal review of all pull requests to ensure alignment with FRs; use of "Deferred/Future Scope" list for new ideas; all changes must be recorded in the Engineering Decision Log. | Re-baseline the project with assessor approval; deprioritize existing "Should Have" features to accommodate new work; escalate to lecturer if necessary. | Member 1 (Scope Owner) | Active |
| R-02 | Schedule Overrun: Failure to complete M1 deliverables on time due to inefficient team communication, unclear task allocation, or underestimation of effort. | Medium | High | High | Create and track GitHub issues for all tasks; adhere to Team Working Agreement; identify blockers early in team meetings; maintain regular communication through the team chat channel. | Re-prioritize tasks to ensure core deliverables (PED, RTM, Registers) are completed; temporarily reduce non-essential artefact polish; request a brief extension if justified. | Member 4 (GitHub/Project Coordinator) | Active |
| R-03 | Technical Complexity: The chosen technology for M2/M3 may prove too complex for the team to implement effectively within schedule constraints, impacting quality. | Medium | Medium | Medium | Conduct a fair technology evaluation in M2; choose a technology with at least some team familiarity; build a small proof-of-concept early before committing fully. | Select an alternative, simpler technology; reduce the scope of features in M3 to match team capability; seek guidance from the lecturer. | Member 3 | Active |
| R-04 | Poor Traceability: The link between requirements, design, and testing evidence becomes broken or unclear, losing the controlled engineering baseline. | Low | High | Medium | Maintain the RTM as a live artefact from M1 onward; update the RTM with design and test evidence in M2 and M3 as soon as it is produced; cross-reference design and test artefacts in commits; use consistent unique IDs. | Audit the RTM and evidence in the final days of M2/M3; add missing links before submission; designate a team member to oversee traceability. | Member 2 (RTM Owner) | Active |
| R-05 | Inadequate Testing: Critical requirements are not adequately tested, leading to a working but unreliable system that fails to meet acceptance criteria. | Low | High | Medium | Write test cases derived directly from acceptance criteria at the same time as design; use the RTM to drive test planning; ensure all "Must Have" requirements have corresponding tests. | Perform a final "smoke test" against the RTM before submission; document any known defects transparently; prioritize testing of "Must Have" features. | Member 2 | Active |
| R-06 | AI Misuse: Team members rely on AI-generated content without verification, introducing errors, inconsistencies, or academic integrity issues into project artefacts. | Low | Medium | Low | Maintain the AI Usage Register as required by the Master Project Brief; enforce the rule that all AI output must be reviewed and verified by a team member; cross-check AI contributions against source materials; cite all external sources. | Revise and resubmit AI-affected work after manual review by another team member; consult the lecturer if clarification is needed on AI use. | Member 4 (AI Register Owner) | Active |
| R-07 | Stakeholder Misalignment: The team's interpretation of stakeholder needs differs from the client's actual expectations, resulting in a system that does not meet its intended purpose. | Medium | High | High | Maintain clear traceability from stakeholder needs to requirements (Section 9); use the RTM to demonstrate the link; seek clarification from the lecturer (acting as client) if ambiguous requirements arise. | Revisit stakeholder analysis and adjust requirements; update the RTM and associated artefacts; communicate changes through the Engineering Decision Log. | Member 1 (Stakeholder/Scope Owner) | Active |
| R-08 | Citizen data exposure caused by incomplete access/data-handling rules. | Medium | High | High | Least privilege, data minimisation, synthetic test data and negative-access tests. | Restrict access, preserve evidence, assess exposure and fix before release. | Member 3 | Active |
| R-09 | Deployment blocked by assumed hosting access, quotas or costs. | Medium | High | High | Validate environment, cost and recovery options in M2. | Use an evaluated alternative; record schedule/scope impact. | Member 3 | Active |

R-01, R-02 and R-07 initially have Medium probability and High impact, giving High priority. R-08 and R-09 are additional High-priority risks. These ordinal ratings prioritise action; they do not establish certainty or catastrophic impact. Owners review ratings at each milestone.

R-01 (Scope Creep) is particularly dangerous because it directly undermines the controlled engineering baseline that M1 is meant to establish. If the team starts adding features beyond what is defined in the Scope Baseline, the requirements will no longer be stable, the RTM will become inaccurate, and the project will lose its controlled foundation. This is why the Scope Baseline includes a deliberate "Deferred/Future Scope" list—to provide a place for new ideas without compromising the current baseline.

R-07 (Stakeholder Misalignment) is equally critical because the entire project is built upon the stakeholder analysis. If the team has misinterpreted what citizens, staff, or the organization actually need, then all subsequent requirements, design decisions, and testing efforts will be misdirected. The RTM traceability example is the primary control against this risk, as it demonstrates a clear chain from stakeholder need to acceptance criteria.

R-02 (Schedule Overrun) is prioritized because failure to complete M1 on time would prevent the team from presenting and defending their work, which is a compulsory requirement for every registered student. The team's use of GitHub issues and protected-main governance are the primary mitigations against this risk.

# 12. Forward Engineering Considerations

The following seven later-lifecycle concerns require attention during M1, without prematurely making decisions or committing to a final solution. These considerations directly influence the requirements, constraints, and risks already identified in this PED. For each concern, the team has considered why it matters now, what later decisions it may influence, what information is still missing, and the risk of ignoring it.

## 12.1 Technology Stack Selection

The choice of programming language, web framework, and database will heavily influence the system's performance, security, and maintainability, directly impacting NFR-02 (Access Control), NFR-03 (Response Time), and NFR-07 (Scalability). This decision also affects the team's ability to implement requirements within the cost/resource and schedule constraints. The technology stack will influence the M2 architecture design, M3 construction, deployment environment, and operational costs. At this stage, however, the team lacks a detailed evaluation of available technologies against our NFRs, as well as clarity on deployment environment restrictions and team familiarity with potential options. Ignoring this concern could result in selecting a technology in M2 without proper consideration, leading to technical debt, poor performance, or a system that is difficult to test or deploy. This risk is already captured as R-03 (Technical Complexity).

## 12.2 Automated Testing Strategy

The testability of the system should be considered alongside the requirements themselves. Our NFRs, particularly NFR-03 on response time and NFR-06 on maintainability, need to be testable, which may require specific tools or design patterns. Testing is essential for verifying acceptance criteria and catching defects early. This concern will influence test planning in M3, code structure, and CI pipeline design. The approach to testing may also influence technology selection. Currently, the team has not yet determined the exact testing framework, the balance between unit, integration, and end-to-end testing, or the level of test coverage required to satisfy M3 expectations. Without a clear testing strategy, the team risks building a system that is difficult to test, leading to low-quality code that does not meet its acceptance criteria (R-05). This could also reduce the team's ability to demonstrate traceability from requirements to test evidence.

## 12.3 Deployment Environment and Operations

The target deployment environment—whether cloud, local, or university server—and the operational requirements (availability NFR-04) impose constraints on the design, architecture, and technology choices. The system must be deployable within the project's resource constraints. This decision will influence technology choice, architecture, scalability (NFR-07), and the CI/CD pipeline. However, the team does not yet know the specific deployment target, operational access rights available, or university policies on hosting. Ignoring this concern could result in a system that cannot be easily deployed to the target environment, or one that lacks necessary capabilities such as logging and monitoring required for operation. This aligns with the schedule constraint, as deployment issues could cause delays in M3.

## 12.4 Data Migration and Recovery

The system will persist data including requests, user accounts, and status updates. The team must therefore consider how data migration will be handled if the data model changes, and what backup and recovery plan will ensure data integrity and availability. These are quality and security concerns. Data migration and recovery will influence database schema design, testing, and operational procedures. At present, the team does not have clarity on the initial data set, the need for data backup or migration scripts, or the acceptable recovery time objective. Ignoring this concern could result in data loss during updates, or the system failing to recover from a database failure, which would lose citizen requests. Such a failure would violate the quality and security constraints and directly relate to NFR-04 (Availability).

## 12.5 Observability and Logging

Once the system is in operation, or even during testing, the team needs to understand what is happening within the system. This includes logging user actions, system errors, and performance metrics to debug issues and ensure security. This is directly relevant to NFR-02 (Access Control) and operational quality. Observability will influence architecture design, logging frameworks, deployment, and operations. The level of logging may also affect performance (NFR-03). The team still needs to determine the level of logging detail required, the tools to be used, and storage and retention policies for logs. Without adequate logging and monitoring, a system that crashes or behaves unexpectedly becomes very difficult to debug, potentially leading to project failure or schedule overrun (R-02). Security breaches may also go undetected.

## 12.6 User Data Privacy

The system handles citizen data including requests and personal information, which raises legal and ethical privacy concerns. This is directly related to NFR-02 (Access Control), the Security Constraints, and the stakeholder conflict between citizen simplicity and organisational control. Privacy concerns will influence architecture, security design, technology selection, and data handling policies. The team does not yet have clarity on specific university, legal, or ethical requirements for handling user data, or on anonymisation or data minimisation requirements. Ignoring this concern could result in a system that is non-compliant with data protection principles, leading to ethical and potential legal issues, not to mention a failing grade. This also reinforces the high priority of R-07 (Stakeholder Misalignment), as the organisation likely has specific privacy expectations that must be understood.

## 12.7 Maintainability and Technical Debt

The system is not a one-off project; the team must build a baseline that is maintainable and traceable to support later changes, as captured in NFR-06. Taking shortcuts now will create technical debt that makes future milestones more difficult and costly. Maintainability will influence code quality, documentation, and RTM traceability, as well as the team's ability to respond to scope changes (R-01). The team still needs to establish clear coding standards and review processes and determine the level of documentation required for maintainability. If maintainability is ignored, the codebase could become messy increasing the time for bug fixes, feature additions, and test execution in M3. This risks schedule overrun (R-02) and poor quality (R-05). The protected-main branch and two-reviewer approval governance model serve as the primary early controls against this risk.

# 13. Relationship to Other Artefacts

This section demonstrates how the constraints, risks, and forward engineering considerations connect to the work of other team members.

| Artefact | Relationship |
| --- | --- |
| Requirements | The Security Constraint justifies why NFR-02 (Access Control) and FR-06 (User Management) are "Must Have" requirements. The Schedule Constraint defers advanced analytics while preserving FR-09 basic oversight. |
| Scope Baseline | The Scope Constraint reinforces the in-scope, out-of-scope, and deferred decisions made by Member 1. The trade-off between Quality and Schedule supports the scope exclusions. |
| Stakeholder Analysis | The stakeholder conflict identified in Section 5 is reflected in the Usability vs. Security trade-off. R-07 (Stakeholder Misalignment) directly references the stakeholder analysis. |
| RTM | R-04 (Poor Traceability) is mitigated by the existence of the RTM and the traceability example in Section 9. The Forward Engineering Consideration on Maintainability reinforces the need for the RTM to remain a live artefact. |
| Engineering Decision Log | Any decision to change scope or accept a risk will be recorded in the Decision Log, as required by the Master Project Brief. The trade-offs identified will also be referenced in the Decision Log. |

# Member 4 – Decisions, GitHub & Project Control

Milestone 1 controlled artefacts and governance evidence

This workstream establishes the project-control evidence required for Milestone 1: the Engineering Decision Log, repository governance model, issue/backlog structure, branch and commit rules, Pull Request and review controls, AI Usage Register, PED v1.0 document control, team review coordination and the baseline gate. The controls below are grounded in the existing CivicConnect PED and the governing SEN381 project briefs.

# 14. Engineering Decision Log

The Engineering Decision Log records significant project decisions so that the team can later explain the context, constraints, alternatives, rationale, trade-offs, risks, supporting evidence and downstream consequences. Draft decisions require dated team confirmation before being treated as accepted. Choices that require evidence from M2 or later are deliberately marked as deferred rather than being guessed prematurely.

| Decision ID | Decision / Deferred Item | Status | Current Evidence |
| --- | --- | --- | --- |
| EDL-001 | Core M1 scope baseline | Team confirmation pending | Sections 4 and 10.1; R-01 |
| EDL-002 | MoSCoW prioritisation and controlled deferral | Team confirmation pending | Sections 6–8 and 10.6 |
| EDL-003 | Security/usability balance | Team confirmation pending | Section 5; FR-06/FR-07; NFR-01/NFR-02 |
| EDL-004 | Mandatory basic oversight; advanced analytics deferred | Proposed correction | Master Section 3; FR-09; review 2026-09-09 |
| EDL-005 | Final technology stack and software architecture | Deferred | Sections 4 and 12.1 |
| EDL-006 | Detailed database, API and UI design/implementation | Deferred | Sections 4 and 12 |
| EDL-007 | Deployment target, CI/testing tooling and notification mechanism | Deferred | Sections 12.2–12.3; FR-08 |

## EDL-001 – Core M1 scope baseline

| Decision ID / Status | EDL-001 / Recorded draft decision; team confirmation pending |
| --- | --- |
| Context | CivicConnect must address the service-request communication problem without expanding M1 into implementation or unrelated organisational systems. |
| Constraints | Fixed milestone schedule, limited team resources, controlled scope, quality and security obligations. |
| Alternatives | Broader feature set; replacement of external organisational systems; production implementation during M1. |
| Decision | Commit M1 to the core service-request lifecycle and associated access, status, role-administration and validation capabilities; exclude unrelated systems and production implementation. |
| Rationale | A smaller controlled baseline preserves traceability and lets the team demonstrate the core stakeholder value before optional enhancements are added. |
| Trade-offs | The team accepts less breadth in exchange for stronger control, clearer testing targets and reduced schedule risk. |
| Risks | Scope creep (R-01) if excluded or deferred work is added without change control. |
| Evidence | Scope Baseline in Section 4; Scope Constraint in Section 10.1; Risk R-01. |
| Later consequence | Any post-baseline scope addition must be analysed and authorised through change control before the baseline and RTM are updated. |

## EDL-002 – MoSCoW prioritisation and controlled deferral

| Decision ID / Status | EDL-002 / Recorded draft decision; team confirmation pending |
| --- | --- |
| Context | Not all requirements can receive equal implementation priority within the fixed schedule and resource limits. |
| Constraints | Schedule, team capacity, quality expectations and stakeholder value. |
| Alternatives | Treat every requirement as equally mandatory; prioritise informally without an explicit scheme. |
| Decision | Use MoSCoW while retaining every master-brief minimum capability, including validation, feedback and basic reporting, as Must Have. Defer additional enhancements or implementation choices. |
| Rationale | The approach makes trade-offs visible and gives the team a controlled basis for deferring lower-value work rather than rushing all features. |
| Trade-offs | Some useful functionality may be delivered later, but core quality is protected. |
| Risks | Stakeholder dissatisfaction if deferred items are assumed to be committed; mitigated by the explicit deferred/future scope list. |
| Evidence | FR/NFR priority tables, prioritisation note, constraint trade-off table and deferred/future scope. |
| Later consequence | M2 and M3 planning must preserve Must Have coverage first; any priority change must update the requirements and RTM. |

## EDL-003 – Security/usability balance

| Decision ID / Status | EDL-003 / Recorded draft decision; team confirmation pending |
| --- | --- |
| Context | Citizens need a simple process while the organisation requires validation, role control and protection of citizen information. |
| Constraints | NFR-01 usability, NFR-02 security, data-quality needs and the stakeholder conflict in Section 5. |
| Alternatives | Minimise controls for simplicity; require excessive information and intrusive controls for security. |
| Decision | Keep citizen-facing mandatory input limited to what is necessary while enforcing validation and role-based access controls as part of the system behaviour. |
| Rationale | The decision protects both accessibility and organisational control rather than treating them as mutually exclusive. |
| Trade-offs | Additional validation and access checks add design/test effort, but reduce privacy and data-quality risk. |
| Risks | Poor usability if controls become too intrusive; security/privacy exposure if controls are weakened. |
| Evidence | Section 5 stakeholder conflict; FR-06, FR-07; NFR-01, NFR-02; Section 10.6 trade-off analysis. |
| Later consequence | M2 architecture and UI decisions must show how security is enforced without adding unnecessary steps to the citizen workflow. |

## EDL-004 Basic oversight scope correction

| Decision ID / Status | EDL-004 / Proposed correction awaiting team approval |
| --- | --- |
| Context | The earlier draft treated basic reporting as optional; the 9 September review found mandatory management capabilities in Master Section 3. |
| Constraints | Minimum capability coverage, schedule and capacity. |
| Alternatives | Retain basic oversight and defer advanced analytics; alternatively request a formally authorised scope variation. Unapproved omission is not acceptable. |
| Decision | Propose FR-09 as Must Have; retain advanced analytics as deferred. |
| Rationale | Aligns scope, requirements, RTM and constraint reasoning with the governing brief. |
| Trade-offs | Basic reporting requires delivery effort; defer advanced enhancements to protect capacity. |
| Risks | R-07 if minimum scope is misunderstood; R-02 if reporting effort is omitted. |
| Evidence | Master brief Section 3; FR-09; Section 4; review dated 2026-09-09. |
| Later consequence | Team confirms correction before baseline; M2 design and M3 tests cover FR-09. Version history preserves the earlier draft. |

## EDL-005 – Final technology stack and architecture deliberately deferred

| Decision ID / Status | EDL-005 / Deferred |
| --- | --- |
| Context | The project needs a technology stack and architecture later, but M1 is explicitly a foundation milestone. |
| Constraints | Technology must be justified against requirements, security, cost, schedule, team capability, deployment and maintainability. |
| Alternatives | Select a preferred stack immediately; copy a familiar stack without analysis; defer pending evaluation. |
| Decision | Do not select the final stack or architecture in M1. Carry the decision into M2 after comparing viable options against the baselined requirements and constraints. |
| Rationale | The team does not yet have sufficient evidence on deployment restrictions, team familiarity, technical trade-offs and architecture consequences. |
| Trade-offs | Deferral delays implementation certainty but prevents premature lock-in and avoidable technical debt. |
| Risks | R-03 Technical Complexity if the later selection is not evidence-based. |
| Evidence | Out-of-scope statement in Section 4; Forward Engineering Consideration 12.1; R-03. |
| Later consequence | M2 must produce a structured decision/ADR with alternatives, evidence and downstream consequences. |

## EDL-006 – Detailed database/API/UI decisions deliberately deferred

| Decision ID / Status | EDL-006 / Deferred |
| --- | --- |
| Context | Persistence, API and UI details will be needed, but they depend on the chosen architecture and refined design evidence. |
| Constraints | M1 boundary, maintainability, data privacy, testability, security and future deployment choices. |
| Alternatives | Design/implement these areas now; create exploratory notes only; defer formal decisions. |
| Decision | Keep detailed database schema, API contracts and UI implementation outside the M1 baseline; record only the requirements, risks and decision criteria that those later designs must satisfy. |
| Rationale | This preserves design options and avoids creating artefacts that may need to be discarded after M2 architecture decisions. |
| Trade-offs | Less implementation detail is available now, but the baseline remains lifecycle-appropriate and defensible. |
| Risks | Later rework if M2 ignores the current NFRs, privacy concerns or RTM links. |
| Evidence | Out-of-scope statement in Section 4; Forward Engineering Considerations 12.2–12.7. |
| Later consequence | M2 design artefacts must link back to requirements and update the RTM/Decision Log as decisions are made. |

## EDL-007 – Deployment, CI/testing tooling and notification mechanism deferred

| Decision ID / Status | EDL-007 / Deferred |
| --- | --- |
| Context | Deployment, automated verification and citizen notification all influence later engineering, but exact mechanisms are not yet supported by sufficient M1 evidence. |
| Constraints | Unknown deployment target/access rights, future technology choice, operational cost, testability and stakeholder communication expectations. |
| Alternatives | Choose tools/channels immediately; keep all options open without recording criteria; defer with explicit evidence needs. |
| Decision | Defer the exact deployment platform, CI/test toolchain and FR-08 notification channel. Preserve the required outcomes and evaluation criteria in the baseline. |
| Rationale | The required behaviour is known, but the implementation mechanisms depend on M2 architecture/technology and stakeholder/platform evidence. |
| Trade-offs | The team cannot yet demonstrate tool-specific implementation, but avoids committing to incompatible or costly options. |
| Risks | Deployment delay, inadequate testing or communication mismatch if these choices are left too late. |
| Evidence | Forward Engineering Considerations 12.2 and 12.3; FR-08; deferred advanced notifications. |
| Later consequence | M2/M3 must convert these deferrals into controlled decisions and link the resulting issue/PR/test/deployment evidence to the RTM. |

# 15. GitHub Repository and Team Governance

GitHub is treated as a configuration-management and engineering-evidence environment. Substantive controlled changes must progress through issues/tasks, branches, meaningful commits and Pull Requests before entering the controlled main branch. The live repository must demonstrate authentic progression rather than reconstructed activity.

| Control | Mandatory Expectation | Applied Project Rule / Current Status | Evidence to Retain |
| --- | --- | --- | --- |
| Repository | One controlled team repository. | Configured: https://github.com/VoidMeBro/SEN381-CivicConnect-Lineup | https://github.com/VoidMeBro/SEN381-CivicConnect-Lineup |
| Main branch | Protected and treated as the controlled product state. | Verified 2026-09-09: PR required; 2 approvals; stale approvals dismissed; conversations resolved; administrators cannot bypass; force pushes/deletion disabled. | https://github.com/VoidMeBro/SEN381-CivicConnect-Lineup/settings/branch_protection_rules/82957015 |
| Direct development on main | Not permitted for substantive controlled changes. | Prohibited by team workflow. | Branch protection + history. |
| Pull Requests | Required for substantive changes entering main. | PR #7 open on docs/member4-project-control; reviews pending. | https://github.com/VoidMeBro/SEN381-CivicConnect-Lineup/pull/7 |
| Approval | Minimum TWO approvals from team members other than the author. | Two approvals enforced; real team reviews pending. | https://github.com/VoidMeBro/SEN381-CivicConnect-Lineup/pull/7 |
| Self-approval | Not accepted. | Prohibited. | Reviewer identities. |
| Review quality | Meaningful engineering review; no rubber-stamping. | Review checklist defined. | Comments, author response and re-review. |
| Issues/tasks | Meaningful work represented in backlog/project board and linked where practical. | Existing issues #1–#6 retained. Section 15.2 contains internal task IDs, not live GitHub issue numbers. | https://github.com/VoidMeBro/SEN381-CivicConnect-Lineup/issues |
| Secrets | No passwords, API keys, tokens, private keys or confidential credentials. | Prohibited; use environment/configuration controls later. | Repository history/settings. |
| History | Commits, PRs, reviews and merges must be progressive and authentic. | Commits a10c26a and c708aae record real upload/control work. No historical progression or reviews are reconstructed. | Commit/PR timeline. |

## 15.1 Proposed Repository Structure

/

├── README.md

├── docs/

│   ├── PED/

│   ├── requirements/

│   ├── decisions/

│   ├── risk/

│   ├── change/

│   ├── quality/

│   ├── security/

│   ├── deployment/

│   └── governance/

├── src/

├── tests/

├── .github/

│   ├── workflows/

│   └── pull_request_template.md

└── .gitignore

The structure is intentionally simple. It separates the evolving PED and controlled engineering records from implementation artefacts while preserving links between requirements, decisions, risks, issues/PRs, tests and deployment evidence.

## 15.2 Internal M1 Task Breakdown

| Internal task ID | Task | Owner / Workstream | Definition of Done |
| --- | --- | --- | --- |
| M1-01 | Baseline problem, stakeholders and scope | Workstream 1 | Problem, stakeholder and scope sections reviewed and linked. |
| M1-02 | Functional and non-functional requirements | Workstream 2 | Priorities, sources and measurable acceptance criteria complete. |
| M1-03 | Initial RTM and traced requirement example | Workstream 2 | All FR/NFR IDs present; one requirement traced end-to-end for M1 evidence. |
| M1-04 | Constraints and trade-off analysis | Workstream 3 | Scope, schedule, cost/resources, quality and security implications recorded. |
| M1-05 | Initial Risk Register | Workstream 3 | Probability, impact, priority, mitigation, contingency, owner and status complete. |
| M1-06 | Forward Engineering Considerations | Workstream 3 | 5–7 project-specific concerns with missing evidence and downstream risks. |
| M1-07 | Engineering Decision Log | Member 4 workstream | Accepted and deferred M1 decisions recorded with evidence and consequences. |
| M1-08 | GitHub governance and protected main | Member 4 workstream | Main protected; PR-only substantive changes; two non-author approvals. |
| M1-09 | AI Usage Register | Member 4 workstream | Material AI use recorded and human verification evidence retained. |
| M1-10 | PED v1.0 control, team review and baseline gate | Member 4 workstream / All | Version history complete; team review resolved; sign-off recorded. |
| M1-11 | M1 baseline correction pass | All | Cross-artefact IDs, scope, RTM, risks, decisions and governance evidence consistent. |

## 15.3 Branch and Commit Standard

Create a branch for every substantive controlled change. M1 documentation branches should use descriptive names such as `docs/member4-project-control` or `docs/M1-<task>-<short-name>`; later feature work may use `feature/FR-XX-<short-name>` and fixes `fix/<issue>-<short-name>`.

Keep branches focused on one coherent issue or change so that the PR can be reviewed meaningfully.

Commits must be small enough to explain, use meaningful messages, and reference the relevant issue/requirement/decision where practical.

Do not use vague messages such as `update`, `final`, `stuff`, `changes` or bulk end-of-milestone commits.

Example commit messages:

docs(M1): add initial engineering decision log [M1-07]

docs(RTM): correct FR-08 traceability link [M1-03]

docs(risk): update R-02 mitigation after schedule review [M1-05]

governance: add PR review template and protected-main checklist [M1-08]

## 15.4 Pull Request and Meaningful Review Standard

Every substantive PR must state the purpose of the change, identify linked issues/requirements/risks/decisions where practical, and show what was checked before merge. Reviewers should explicitly consider:

Alignment with requirements and acceptance criteria.

Correctness, internal consistency and design/document consistency.

Maintainability and technical-debt impact.

Security and privacy implications.

Test and regression implications, where applicable.

Dependency changes, where applicable.

Documentation and traceability impact.

Whether the change is suitable to enter the controlled baseline.

Required review path:

Review comment  →  Author response  →  Correction  →  Re-review  →  TWO approvals  →  Merge

## 15.5 Protected Main Branch Configuration Checklist

| Setting | Configuration | Engineering Purpose |
| --- | --- | --- |
| Require a Pull Request before merging | ON | Prevents substantive direct-to-main changes. |
| Required approving reviews | 2 | Both approvals must be from team members other than the author. |
| Dismiss/refresh approval after material changes | Recommended ON | Ensures approval still applies to the current change. |
| Require conversation resolution before merge | Recommended ON | Prevents unresolved review concerns being bypassed. |
| Restrict force pushes | ON / not allowed | Protects the controlled history. |
| Restrict branch deletion | ON / not allowed | Prevents accidental loss of the controlled branch. |
| Direct commits to main | Not allowed for substantive work | All controlled changes enter through PRs. |

Evidence should be presented from the live repository/settings where practical. A screenshot may support the PED, but the live settings, PR history, reviews and issue links are stronger assessment evidence.

# 16. AI Usage Register

Material AI-assisted work is recorded because AI output is not authoritative evidence and does not transfer accountability away from the team. Each entry must identify what AI contributed, how a human verified it, what was accepted/rejected, and any issues discovered.

## 16.1 Register Entry AI-001

| Date | 2026-09-09 |
| --- | --- |
| Student | Member 4 coordinator, GitHub VoidMeBro; full student name/number to be recorded by team. |
| Tool | ChatGPT |
| Engineering task | Draft the M1 Engineering Decision Log, GitHub governance controls, AI Usage Register structure, PED document control and baseline-gate material from the supplied project briefs and existing CivicConnect draft. |
| AI contribution | Proposed controlled structures, drafted decision records from existing PED evidence, created GitHub workflow/checklists/templates, and identified unresolved governance conditions. |
| Verification | PENDING HUMAN VERIFICATION. A registered team member must manually cross-check this entry and the generated artefacts against the SEN381 Master Project Brief, the M1 brief and the existing PED. The generated text must be edited where project facts or live repository evidence differ. |
| Decision | Accepted as a draft for team review only; not yet approved as baselined evidence. |
| Issues found | Initial draft lacked live GitHub evidence and used inconsistent team-size wording. Repository controls were subsequently verified on 2026-09-09. The user confirms four members; lecturer registration/exception evidence remains to be attached because the briefs specify three. |

## 16.2 Human Verification Checklist for AI-001

| Verification Item | Human Check Required | Status |
| --- | --- | --- |
| Project-brief requirements | Check GitHub, AI, decision-log and sign-off fields against the governing brief. | Pending |
| Project facts | Confirm every decision record matches an actual M1 decision or justified deferral. | Pending |
| Existing PED links | Confirm requirement IDs, scope items, risks and section references are correct. | Pending |
| Live GitHub evidence | Replace 'pending' statuses with live links/settings only after controls actually exist. | Pending |
| Language and ownership | Edit any wording the team cannot personally explain or defend. | Pending |
| Final human decision | Mark AI-001 Accepted / Modified / Rejected and record issues found. | Pending |

Additional material AI use by any team member must be added as a new register entry. The register should not be limited to this entry if AI assisted requirements, research, code, testing, debugging, review or documentation elsewhere in the project.

# 17. PED v1.0 Version and Document Control

The Project Engineering Document is a single evolving controlled record. M1 establishes the v1.0 engineering baseline; later milestones update the same PED rather than replacing it with unrelated reports.

| Document Title | CivicConnect Project Engineering Document – Milestone 1 Engineering Baseline |
| --- | --- |
| Document Identifier | PED-CIVIC-M1 |
| Planned Baseline Version | v1.0 |
| Current Control State | v0.10 corrected candidate; team review and baseline gate pending |
| Document Owner | Project Control workstream (Member 4 label); final ownership remains collective |
| Governing Documents | SEN381 CivicConnect Master Project Brief and Milestone 1 brief |
| Controlled Repository Location | /docs/PED/CivicConnect_Milestone1_With_Member4.docx; branch docs/member4-project-control; PR #7 |
| Review Frequency | Before M1 sign-off and at every later milestone update |
| Post-baseline Change Rule | Do not silently overwrite baselined content. Approved changes must be linked to change records and affected artefacts/RTM. |

## 17.1 Version History

| Version | Date | Purpose / Change Summary | Status |
| --- | --- | --- | --- |
| 0.9 | 2026-09-09 | Integrated M1 working draft containing existing PED sections plus Member 4 control artefacts. | Draft for team review |
| 0.10 | 2026-09-09 | Correct mandatory capabilities, criteria, RTM, team records and GitHub evidence; add AI entries and review agreement. | Review candidate; supersedes 0.9 working copy |
| 1.0 | To be entered at sign-off | M1 Engineering Foundation & Requirements Baseline accepted as the controlled baseline. | Pending baseline gate |

## 17.2 Controlled Document Rules

Use stable identifiers for requirements, risks, decisions, changes, tests and defects.

Preserve version history, authorship, review and approval information.

Do not silently overwrite baselined scope or requirements after sign-off.

Link approved changes to the RTM and all affected engineering artefacts.

Use repository/PR history as the primary evidence of controlled document evolution.

Support major quality, security, performance and readiness claims with measurable or traceable evidence.

# 18. Team Review, Baseline Sign-Off and Gate Evidence

Before PED v1.0 is signed off, the registered team should perform a coordinated review across the complete baseline rather than reviewing sections in isolation. The purpose is to verify consistency between stakeholder needs, scope, requirements, RTM, constraints, risks, decisions, repository governance and AI accountability.

## 18.1 Pre-Sign-Off Review Checklist

| Review Area | Review Expectation | Current Readiness |
| --- | --- | --- |
| Problem / stakeholder / scope | Present and linked to the CivicConnect business need. | Prepared; substantive team review pending |
| FRs / NFRs / acceptance criteria | Unique IDs, priorities, sources and measurable criteria are present. | Prepared; substantive team review pending |
| RTM | All current requirements represented; traced example available. | Prepared; substantive team review pending |
| Constraints and trade-offs | Scope, schedule, cost/resources, quality and security analysed. | Prepared; substantive team review pending |
| Risk Register | Probability, impact, priority, mitigation, contingency, owner and status recorded. | Prepared; substantive team review pending |
| Engineering Decision Log | Accepted decisions and justified deferrals recorded with evidence. | Prepared; substantive team review pending |
| GitHub governance | Protected main, PR-only substantive changes, two non-author approvals and progressive evidence. | Settings verified; PR #7 awaits two non-author approvals. |
| AI Usage Register | Material AI use recorded with human verification and decision. | AI-001–AI-003 recorded; human verification pending. |
| PED version/document control | Version history and post-baseline change rules defined. | Prepared; substantive team review pending |
| Team registration / role naming | PED ownership labels match the registered team. | Four members confirmed by user; attach lecturer registration/exception evidence. |

## 18.2 Formal Baseline Sign-Off Record

| Project | CivicConnect |
| --- | --- |
| Baseline Type | Milestone 1 – Engineering Foundation & Requirements Baseline |
| Version | v1.0 |
| Date | ____________________________ |
| Scope reviewed | YES / NO |
| Requirements / traceability checked | YES / NO |
| Risk review completed | YES / NO |
| Repository / governance controls checked | YES / NO |
| Outcome | ACCEPTED / CONDITIONALLY ACCEPTED / REVISION REQUIRED |

Registered team review / approval evidence:

| Registered Team Reviewer | Name | Date | Review Outcome |
| --- | --- | --- | --- |
| Reviewer 1 | ____________________________ | ____________________________ | Approve / Changes Required |
| Reviewer 2 | ____________________________ | ____________________________ | Approve / Changes Required |
| Reviewer 3 | ____________________________ | ____________________________ | Approve / Changes Required |
| Reviewer 4 | Team to complete | Team to complete | Approve / Changes Required |

## 18.3 Current Internal Gate Readiness

Current recommendation: REVISION REQUIRED before formal sign-off.

This is internal readiness, not an assessor decision. Repository controls are configured and content corrections prepared. Before v1.0, all four members must verify requirements and targets, resolve findings, complete AI verification, retain four-person registration evidence and obtain two non-author PR approvals. Record the exact approved revision and dates; the assessor gate is separate.

## 18.4 Evidence to Present at M1

Live Engineering Decision Log; defend one accepted decision and one deliberately deferred decision.

Live GitHub repository/settings showing protected main and the PR/review model.

PR #7 and subsequent substantive PRs with genuine findings, responses and two non-author approvals before merge.

Issue/backlog evidence showing authentic task progression.

AI Usage Register with at least one material AI-assisted contribution and completed human verification.

PED v1.0 version history and the completed baseline sign-off/gate record.

# 19 Requirement Definitions and Validation Assumptions

These are proposed engineering targets for team/client validation, not claims of approved stakeholder agreement. Record acceptance or modification before v1.0. Implementation mechanisms remain deferred.

| Topic | Proposed definition |
| --- | --- |
| Input | Title 5–120 characters; description 10–2000; location 3–200; active category; system-derived identity/time. Trim whitespace; reject blank-only values. M2 defines accessible guidance and safe text handling. |
| Lifecycle | Submitted → Accepted → In Progress → Resolved → Closed; Submitted → Rejected. Closed/Rejected are terminal. Reopening requires stakeholder clarification and controlled change. |
| Oversight | Open = Submitted, Accepted or In Progress. Overdue = open with due time passed. Authorised staff set a due time later than submission at acceptance; due-time changes record actor/time/reason. Unaccepted requests without a due time remain visible as untriaged. |
| Due-time policy | Operational planning dates do not imply contractual service-level agreements. Validate authority and policy with client before baseline. |
| Categories | Review an initial list such as facilities, maintenance, IT support and security concerns from the scenario; approve the vocabulary before baseline. |
| Quality targets | Validate NFR-01/03/04/07 targets for stakeholder relevance, feasibility and cost; retain actual decisions and revise linked records if changed. |
| Sources | Master Section 3 supplies mandatory capabilities; stakeholder needs are interpreted from the scenario. Numerical targets and lifecycle rules are team proposals, not interview evidence. |

# 20 Traceability Extension and Change Control

This companion extends the single RTM in Section 8. Pending means evidence has not yet been produced; no implementation or acceptance is claimed.

| Requirement | Change and issue or PR | Implementation | Acceptance and release |
| --- | --- | --- | --- |
| FR-01 | v0.10 correction: PR #7; later change IDs pending | Pending M3 | Pending acceptance and M4 release |
| FR-02 | v0.10 correction: PR #7; later change IDs pending | Pending M3 | Pending acceptance and M4 release |
| FR-03 | v0.10 correction: PR #7; later change IDs pending | Pending M3 | Pending acceptance and M4 release |
| FR-04 | v0.10 correction: PR #7; later change IDs pending | Pending M3 | Pending acceptance and M4 release |
| FR-05 | v0.10 correction: PR #7; later change IDs pending | Pending M3 | Pending acceptance and M4 release |
| FR-06 | v0.10 correction: PR #7; later change IDs pending | Pending M3 | Pending acceptance and M4 release |
| FR-07 | v0.10 correction: PR #7; later change IDs pending | Pending M3 | Pending acceptance and M4 release |
| FR-08 | v0.10 correction: PR #7; later change IDs pending | Pending M3 | Pending acceptance and M4 release |
| FR-09 | v0.10 correction: PR #7; later change IDs pending | Pending M3 | Pending acceptance and M4 release |
| NFR-01 | v0.10 correction: PR #7; later change IDs pending | Pending M3 | Pending acceptance and M4 release |
| NFR-02 | v0.10 correction: PR #7; later change IDs pending | Pending M3 | Pending acceptance and M4 release |
| NFR-03 | v0.10 correction: PR #7; later change IDs pending | Pending M3 | Pending acceptance and M4 release |
| NFR-04 | v0.10 correction: PR #7; later change IDs pending | Pending M3 | Pending acceptance and M4 release |
| NFR-05 | v0.10 correction: PR #7; later change IDs pending | Pending M3 | Pending acceptance and M4 release |
| NFR-06 | v0.10 correction: PR #7; later change IDs pending | Pending M3 | Pending acceptance and M4 release |
| NFR-07 | v0.10 correction: PR #7; later change IDs pending | Pending M3 | Pending acceptance and M4 release |
| FR-10 | v0.10 correction: PR #7; later change IDs pending | Pending M3 | Pending acceptance and M4 release |
| FR-11 | v0.10 correction: PR #7; later change IDs pending | Pending M3 | Pending acceptance and M4 release |
| FR-12 | v0.10 correction: PR #7; later change IDs pending | Pending M3 | Pending acceptance and M4 release |
| FR-13 | v0.10 correction: PR #7; later change IDs pending | Pending M3 | Pending acceptance and M4 release |

After baseline, record change ID, requester/date, reason/value, affected requirements and design/UI/API/data, security/privacy, tests, scope, schedule/resources, cost and risks; propose accept/modify/defer/reject and record authorised outcome/rationale. Implement on a branch, update RTM and related artefacts, obtain two non-author approvals and identify the new revision. An EDL entry does not replace change-impact analysis.

# 21 Four Member Working Agreement and Review Plan

This agreement is proposed for confirmation by all four members. It does not claim attendance, consent or past review activity.

| Member | Responsibility | Identity record |
| --- | --- | --- |
| 1 | Problem, stakeholders and scope; R-01/R-07 | Full name, student number, GitHub account: team to enter |
| 2 | Requirements, RTM and acceptance; R-04/R-05 | Full name, student number, GitHub account: team to enter |
| 3 | Constraints, risks, forward considerations; R-03/R-08/R-09 | Full name, student number, GitHub account: team to enter |
| 4 | Decisions, repository and AI controls; R-02/R-06 | GitHub VoidMeBro; full name/student number: team to enter |

The user confirms four members. Master Section 7.1 and the M1 cover specify three. Retain the real allocation and attach lecturer registration/exception evidence before claiming compliance.

Proposed cadence: twice-weekly progress checks in the agreed team channel; raise blockers within one working day. Record attendance, tasks, owners, next actions and outcomes. All members contribute and defend the whole PED. Use existing issues or internal task records; no new issues are created for this correction.

Each PR author identifies two other members with write access. They review correctness, requirements, traceability, security and AI claims, record findings, and approve after resolution. The fourth member may also review. No self/proxy approval. Member 4 coordinates review; unresolved disagreements are documented and escalated to the lecturer where necessary.

| Review | Responsible people | Evidence |
| --- | --- | --- |
| Scope/requirements | Members 1 and 2; others cross-check | Master Section 3 coverage and acceptance/modification of Section 19 |
| Constraints/risks | Member 3 and owners | Ratings, feasibility, mitigation and accountable owner confirmed |
| Decision/AI | Member 4 and non-author reviewers | EDL confirmation and named AI-001–AI-003 verification |
| Whole PED/PR | Two non-author reviewers and all four participants | PR links, resolved findings, exact approved SHA and sign-off |
| Baseline gate | Team; assessor gate separately | Date/version, outcomes, conditions and genuine evidence |

# 22 Schedule Resource and Risk Controls

| Milestone | Planning output | Evidence to enter |
| --- | --- | --- |
| M1 | Foundation baseline | Official due date and per-member available hours |
| M2 | Architecture/design and deferred decisions | Official due date and effort estimates |
| M3 | Construction/testing and release readiness | Official due date and effort estimates |
| M4 | Product evaluation and defence | Official due date and effort estimates |

Use confirmed course dates; do not infer deadlines from document dates. The no-budget/free-tier plan is an assumption to validate. M2 compares quotas, licensing, hosting, storage, backup, maintenance effort and environment access before commitment.

Risk scale: probability Low = unlikely, Medium = plausible, High = likely without intervention. Impact Low = local rework, Medium = material task/quality delay, High = milestone or mandatory-outcome threat. Priority: Low/Low and Low/Medium = Low; Low/High, Medium/Low, Medium/Medium and High/Low = Medium; Medium/High, High/Medium and High/High = High. Re-rate when evidence changes.

Member 3 revisits EDL-005/006 at M2 design review. EDL-007 platform/tool evidence is gathered in M2 before M3, with Member 2 on testing and Member 1 on feedback outcomes. Escalate missing evidence threatening the next milestone; record date, evidence and outcome when each deferral is resolved.

# 23 Additional AI Usage Records

| Field | Record |
| --- | --- |
| ID | AI-002 |
| Date | 2026-09-09 |
| Student | Member 4, VoidMeBro; full name/student number to be entered |
| Tool | OpenAI Codex |
| Engineering task | Repository setup |
| AI contribution | Codex inspected GitHub, created the task branch and initial issues before the no-more-issues instruction, README, PR template, PR #7 and controls; uploaded v0.9 unchanged. |
| Verification | Source hash comparison, git checks, saved-rule inspection and GitHub merge-block verification; these are automated checks, not human sign-off. |
| Decision | Proposed for human review; acceptance pending |
| Issues found | Integration writes unavailable; browser/git used. No approvals or history fabricated. |
| Human record | Verifier/name/date; checks and findings; accepted/modified/rejected items and evidence link: team to complete |

| Field | Record |
| --- | --- |
| ID | AI-003 |
| Date | 2026-09-09 |
| Student | Member 4, VoidMeBro; full name/student number to be entered |
| Tool | OpenAI Codex |
| Engineering task | Content audit and v0.10 correction |
| AI contribution | Codex compared both briefs, proposed missing requirements/targets and corrected scope, RTM, decisions, team records and evidence. |
| Verification | Programmatic ID/RTM/structure checks. Human team/client validation of targets and assumptions remains required. |
| Decision | Proposed for human review; acceptance pending |
| Issues found | Missing capabilities, optional basic reporting, premature Baselined status and stale GitHub/team wording corrected. Rendering unavailable in this runtime; visual review remains pending. |
| Human record | Verifier/name/date; checks and findings; accepted/modified/rejected items and evidence link: team to complete |

# 24 Baseline Evidence Completion Record

| Record | Status and completion field |
| --- | --- |
| Candidate | v0.10 in PR #7; record exact final reviewed commit SHA. |
| Registration | Four members confirmed by user; attach lecturer registration/exception. |
| Human verification | AI-001–AI-003: named verifier/date/method/findings/decision pending. |
| Agreement/targets | Four members confirm Section 21; validate Section 19 with client/lecturer. |
| Approvals | Two non-author PR reviews pending; retain findings, resolutions and links. |
| Visual review | Open corrected DOCX in Word and check every page/table before submission; automated rendering unavailable. |
| Team sign-off | Complete Section 18.2 for four members with date, exact version and conditions. |
| Assessor gate | Pending assessment; record issued ACCEPTED / CONDITIONALLY ACCEPTED / REVISION REQUIRED with date/evidence separately from team readiness. |

# 25 References

SEN381 CivicConnect Master Project Brief 2026: Sections 3, 7.1, 8–14, 18 and Appendix D. SEN381 Milestone 1: Sections 3–5 and 9. Supplied CivicConnect_Milestone1_With_Member4.docx v0.9: source draft. No unrecorded stakeholder interviews or approvals are claimed.

Repository: https://github.com/VoidMeBro/SEN381-CivicConnect-Lineup

Review: https://github.com/VoidMeBro/SEN381-CivicConnect-Lineup/pull/7

Verified protection: https://github.com/VoidMeBro/SEN381-CivicConnect-Lineup/settings/branch_protection_rules/82957015

Control record: https://github.com/VoidMeBro/SEN381-CivicConnect-Lineup/blob/docs/member4-project-control/docs/Repository_Control.md